## Slide 1: PPL1.6 Pumping Plant Project Overview
John O’Callaghan, Assistant Manager, Technical Services
South Columbia Basin Irrigation District

## Slide 3: Description
The PPL1.6 Pumping Plant lifts waste, seepage and return flow project water, which would otherwise be lost to the Columbia River, from the Esquatzel Diversion Canal up into the Pasco Pump Lateral, serving irrigation demand for Block 1.

## Slide 4: Summary
Engineering and Construction Services
  RH2 Engineers, Richland, Washington
General Contractor
  Apollo, Inc., Kennewick, Washington
Bureau of Reclamation
  Engineering Review and Approval
  NEPA & NHPA Compliance
Total Cost to Date - $5,032,484

## Slide 5: Benefits
Irrigation Water Supply
  Block 1 supply during peak demand
  Increase available supply upstream during peak demand
Operational
  Reduces stress and demand on upstream system
  Provides operational flexibility during aquatic herbicide applications in the lower Potholes Canal

## Slide 6: Benefits (cont)
Conservation
  Potential reuse in excess of 30,000 acre-feet of project waste, seepage and return flow
Terminal System Management
  Allows for enhanced operational response to downstream issues in an urbanising, high risk service area

## Slide 7: Site – Pre Construction

## Slide 8: Site – Post Construction

## Slide 10: Timeline
Chart: 
| Applied for BPA funds | BPA Agreement $1.526M | RH2 Contract | Reclamation MOA | RH2 #1 | Physical Model | RH2 #2 & #3 | Apollo Contract | Apollo Limited NTP | Apollo Full NTP | First Pump Operation | Commissioning | Receipt of BPA Funds | Operational Testing | Official Completion
POSITION | 25 | 20 | -20 | 15 | -17 | -13 | -17 | 20 | 15 | 10 | -20 | -15 | 20 | -13 | 25
DATE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 11: Timeline and Milestones
SCBID Letter of Intent sent to Reclamation
  06/26/2008
BPA Incentive Payment
  Application – 08/27/2015
  Agreement Signed – 10/23/2015
  Amount of $1,526,425

## Slide 12: Timeline and Milestones (cont)
Reclamation Memorandum of Agreement
  Signed – 02/17/2016
Engineering – RH2 Engineering
  Professional Services Agreement – 12/07/2015
  Amendment #1 – 05/19/2016
  Amendment #2 – 11/21/2016
  Amendment #3 – 11/21/2016

## Slide 13: Timeline and Milestones (cont)
Physical Model Development
  Northwest Hydraulic Consultants
  Model Test Runs – 07/2016
  Final Report – 09/09/2016
Apollo Inc. Contract
  Contract Executed – 12/20/2016
  Limited Notice to Proceed – 12/27/2016
  Full Notice to Proceed – 01/23/2017

## Slide 17: Timeline and Milestones (cont)
Completion Phase
  First Pump Operation – 09/12/2017
  Systems Commissioning – 10/2017
  BPA Approval/Release of Funds – 11/13/2017
  Operations Commence – 04/2018
  Official Completion Date – 06/08/2018

## Slide 19: Challenges
BPA Incentive Payment Timeframe
NEPA
Engineering Review
Costs

## Slide 20
Questions?
John O’Callaghan
jocallaghan@scbid.org
509-547-1735